## Config
📋 PROJECT CONFIGURATION
Project List |  | Instructions
ODC Cleanup |  | 1. Add new project names to column A (starting row 4)
Datastore Reclamation |  | 2. Keep names EXACTLY matching the sheet tab names
Retired VM Cleanup |  | 3. Delete project names when projects are removed
Zerto Scripts |  | 4. Dashboard and Demos will auto-update
5. Maximum supported: 20 projects
4
← Add more projects above

## Dashboard
PROJECT PERFORMANCE DASHBOARD V3
Total Actions | 76
Completed | 0
In Progress | 0
Overdue | 1
Not Started | 75
CHALLENGES TRACKER
Project Name | Total | Completed | In Progress | Overdue | Not Started | Overall Progress | Project Name | % with Challenges
ODC Cleanup | 19 | 0 | 0 | 1 | 18 | 0% | ODC Cleanup | 5.263%
Datastore Reclamation | 19 | 0 | 0 | 0 | 19 | 0% | Datastore Reclamation | 0%
Retired VM Cleanup | 19 | 0 | 0 | 0 | 19 | 0% | Retired VM Cleanup | 0%
Zerto Scripts | 19 | 0 | 0 | 0 | 19 | 0% | Zerto Scripts | 0%

## Demos
📊 PROJECT PORTFOLIO ANALYTICS DASHBOARD
Generated: Dynamic ¦ Data Source: All Project Sheets via Config
🎯 PORTFOLIO KPIs | [6 empty] | Status Breakdown
KPI Metric | Value | Description |  |  |  |  | Completed | 0
Total Projects | 4 | Count of project sheets |  |  |  |  | In Progress | 0
Total Action Items | 76 | Sum of all items (minus headers) |  |  |  |  | Overdue | 1
Completed Items | 0 | Items with Completed status |  |  |  |  | Not Started | 75
In Progress Items | 0 | Items currently In Progress
Overdue Items | 1 | Items marked Overdue |  |  |  |  | Health Scores
Not Started Items | 75 | Items Not Started |  |  |  |  | ODC Cleanup | 0.47368
Overall Completion Rate | 0% | Completed / Total Items |  |  |  |  | Datastore Reclamation | 0.5
[7 empty] | Retired VM Cleanup | 0.5
📋 PROJECT STATUS BREAKDOWN | [6 empty] | Zerto Scripts | 0.5
Project Name | Total | Completed | In Progress | Overdue | Not Started | Progress %
ODC Cleanup | 19 | 0 | 0 | 1 | 18 | 0%
Datastore Reclamation | 19 | 0 | 0 | 0 | 19 | 0%
Retired VM Cleanup | 19 | 0 | 0 | 0 | 19 | 0%
Zerto Scripts | 19 | 0 | 0 | 0 | 19 | 0%
TOTALS | 76 | 0 | 0 | 1 | 75 | 0%
🏷️ PRIORITY CLASS DISTRIBUTION
Project | Must | Should | Could | Wont | Want
ODC Cleanup | 0 | 1 | 0 | 1 | 0
Datastore Reclamation | 0 | 2 | 0 | 1 | 1
Retired VM Cleanup | 0 | 0 | 0 | 0 | 0
Zerto Scripts | 0 | 0 | 0 | 0 | 0
TOTALS | 0 | 3 | 0 | 2 | 1
📊 PHASE DISTRIBUTION
Project | Planning | Requirements | Design | Implementation | Monitoring
ODC Cleanup | 4 | 5 | 2 | 4 | 4
Datastore Reclamation | 4 | 5 | 2 | 4 | 4
Retired VM Cleanup | 4 | 5 | 2 | 4 | 4
Zerto Scripts | 4 | 5 | 2 | 4 | 4
TOTALS | 16 | 20 | 8 | 16 | 16
👤 RESPONSIBILITY BREAKDOWN
Project | Required | Should Have | % Required
ODC Cleanup | 13 | 2 | 68.42%
Datastore Reclamation | 19 | 0 | 100%
Retired VM Cleanup | 19 | 0 | 100%
Zerto Scripts | 19 | 0 | 100%
TOTALS | 70 | 2 | 97.22%
⚠️ CHALLENGES TRACKER
Project | No Challenges | Has Challenges | % with Challenges
ODC Cleanup | 18 | 1 | 5.263%
Datastore Reclamation | 19 | 0 | 0%
Retired VM Cleanup | 19 | 0 | 0%
Zerto Scripts | 19 | 0 | 0%
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
TOTALS | 75 | 1 | 1.316%
📅 TIMELINE TRACKER
Project | Earliest Due | Latest Due | Days Until Due | Items Due This Week
ODC Cleanup | 2026-05-02 23:57 | 2026-05-02 23:57 | 10.9976 | 0
Datastore Reclamation | 2026-05-02 23:57 | 2026-05-02 23:57 | 10.9976 | 0
Retired VM Cleanup | 2026-05-02 23:57 | 2026-05-02 23:57 | 10.9976 | 0
Zerto Scripts | 2026-05-02 23:57 | 2026-05-02 23:57 | 10.9976 | 0
PORTFOLIO SUMMARY | 2026-05-02 23:57 | 2026-05-02 23:57 | 10.9976 | 0
🔥 PRIORITY LEVEL DISTRIBUTION
Project | High | Medium | Low | % High Priority
ODC Cleanup | 0 | 18 | 1 | 0%
Datastore Reclamation | 0 | 19 | 0 | 0%
Retired VM Cleanup | 0 | 19 | 0 | 0%
Zerto Scripts | 0 | 19 | 0 | 0%
TOTALS | 0 | 75 | 1 | 0%
📈 COMPLETION MATRIX (Status x Phase)
Phase \ Status | Not Started | In Progress | Completed | Overdue | TOTAL
Planning | 16 | 0 | 0 | 0 | 16
Requirements | 20 | 0 | 0 | 0 | 20
Design | 8 | 0 | 0 | 0 | 8
Implementation | 15 | 0 | 0 | 1 | 16
Monitoring | 16 | 0 | 0 | 0 | 16
TOTAL | 75 | 0 | 0 | 1 | 76
🏥 PROJECT HEALTH SCORECARD
Project | Completion % | On-Time % | No Challenges % | Must Priority Done % | Health Score
ODC Cleanup | 0% | 94.74% | 94.74% | 0% | 47.37%
Datastore Reclamation | 0% | 100% | 100% | 0% | 50%
Retired VM Cleanup | 0% | 100% | 100% | 0% | 50%
Zerto Scripts | 0% | 100% | 100% | 0% | 50%
PORTFOLIO AVG | 0% | 98.68% | 98.68% | 0% | 49.34%
📖 QUICK REFERENCE LEGEND
Status Values: | Not Started, In Progress, Completed, Overdue
Priority Class (MoSCoW): | Must, Should, Could, Wont, Want
Phases: | Planning, Requirements, Design, Implementation, Monitoring
Priority Levels: | High, Medium, Low
Health Score: | Average of Completion %, On-Time %, No Challenges %, Must Priority Done %
Formulas:
Must = MIN(B136:[Must, row above])
Should = MAX(C136:[Should, row above])

## ODC Cleanup
Action Item | Status | Phase | Category | Priority | Owner | Responsibility | Assigned Date | Due Date | Challenges | Progress % | Priority Class
Project Start | Not Started | Planning | admin | Medium | Owner | required | 2026-04-18 23:57 | 2026-05-02 23:57 |  | 0% | Should
- Create Project Sheet | Not Started | Planning | admin | Medium | Owner | required | 2026-04-18 23:57 | 2026-05-02 23:57 |  | 0%
- Create Confluence Project Page | Not Started | Planning | admin | Medium | Owner | required | 2026-04-18 23:57 | 2026-05-02 23:57 |  | 0% | Wont
- Review Acceptance Criteria | Not Started | Planning | admin | Medium | Owner | required | 2026-04-18 23:57 | 2026-05-02 23:57 |  | 0%
Requirements Gathering | Not Started | Requirements | admin | Medium | Owner | required | 2026-04-18 23:57 | 2026-05-02 23:57 |  | 0%
- Meeting with Stakeholders | Not Started | Requirements | admin | Medium | Owner | required | 2026-04-18 23:57 | 2026-05-02 23:57 |  | 0%
- Refine Acceptance Criteria | Not Started | Requirements | admin | Medium | Owner | required | 2026-04-18 23:57 | 2026-05-02 23:57 | Abbey is hurting me | 0%
- Define MVP | Not Started | Requirements | admin | Medium | Owner | required | 2026-04-18 23:57 | 2026-05-02 23:57 |  | 0%
- Define FR, NFR, AC, US | Not Started | Requirements | admin | Medium | Owner | required | 2026-04-18 23:57 | 2026-05-02 23:57 |  | 0%
Design | Not Started | Design | admin | Medium | Owner | required | 2026-04-18 23:57 | 2026-05-02 23:57 |  | 0%
- Draw C4 Docs | Not Started | Design | admin | Medium | Owner | should have | 2026-04-18 23:57 | 2026-05-02 23:57 |  | 0%
Implementation | Not Started | Implementation | admin | Medium | Owner | required | 2026-04-18 23:57 | 2026-05-02 23:57 |  | 0%
- Create Doctor Patient | Not Started | Implementation | admin | Medium | Owner | required | 2026-04-18 23:57 | 2026-05-02 23:57 |  | 0%
- PR to Main | Overdue | Implementation | admin | Medium | Owner | nice to have | 2026-04-18 23:57 | 2026-05-02 23:57 |  | 0%
- ReadMe | Not Started | Implementation | admin | Medium | Owner | should have | 2026-04-18 23:57 | 2026-05-02 23:57 |  | 0%
Monitoring | Not Started | Monitoring | admin | Medium | Owner | required | 2026-04-18 23:57 | 2026-05-02 23:57 |  | 0%
- Splunk Forwarder Configured | Not Started | Monitoring | admin | Medium | Owner | nice to have | 2026-04-18 23:57 | 2026-05-02 23:57 |  | 0%
- Splunk Dashboard | Not Started | Monitoring | admin | Low | Owner | nice to have | 2026-04-18 23:57 | 2026-05-02 23:57 |  | 0%
- Dynatrace Telemetry | Not Started | Monitoring | admin | Medium | Owner | nice to have | 2026-04-18 23:57 | 2026-05-02 23:57 |  | 0%

## Datastore Reclamation
Action Item | Status | Phase | Category | Priority | Owner | Responsibility | Assigned Date | Due Date | Challenges | Progress % | Priority Class
Project Start | Not Started | Planning | admin | Medium | Owner | required | 2026-04-18 23:57 | 2026-05-02 23:57 | None | 0%
- Create Project Sheet | Not Started | Planning | admin | Medium | Owner | required | 2026-04-18 23:57 | 2026-05-02 23:57 | None | 0%
- Create Confluence Project Page | Not Started | Planning | admin | Medium | Owner | required | 2026-04-18 23:57 | 2026-05-02 23:57 | None | 0%
- Review Acceptance Criteria | Not Started | Planning | admin | Medium | Owner | required | 2026-04-18 23:57 | 2026-05-02 23:57 | None | 0%
Requirements Gathering | Not Started | Requirements | admin | Medium | Owner | required | 2026-04-18 23:57 | 2026-05-02 23:57 | None | 0%
- Meeting with Stakeholders | Not Started | Requirements | admin | Medium | Owner | required | 2026-04-18 23:57 | 2026-05-02 23:57 | None | 0%
- Refine Acceptance Criteria | Not Started | Requirements | admin | Medium | Owner | required | 2026-04-18 23:57 | 2026-05-02 23:57 | None | 0%
- Define MVP | Not Started | Requirements | admin | Medium | Owner | required | 2026-04-18 23:57 | 2026-05-02 23:57 | None | 0%
- Define FR, NFR, AC, US | Not Started | Requirements | admin | Medium | Owner | required | 2026-04-18 23:57 | 2026-05-02 23:57 | None | 0% | Wont
Design | Not Started | Design | admin | Medium | Owner | required | 2026-04-18 23:57 | 2026-05-02 23:57 | None | 0%
- Draw C4 Docs | Not Started | Design | admin | Medium | Owner | required | 2026-04-18 23:57 | 2026-05-02 23:57 | None | 0%
Implementation | Not Started | Implementation | admin | Medium | Owner | required | 2026-04-18 23:57 | 2026-05-02 23:57 | None | 0%
- Create Doctor Patient | Not Started | Implementation | admin | Medium | Owner | required | 2026-04-18 23:57 | 2026-05-02 23:57 | None | 0%
- PR to Main | Not Started | Implementation | admin | Medium | Owner | required | 2026-04-18 23:57 | 2026-05-02 23:57 | None | 0%
- ReadMe | Not Started | Implementation | admin | Medium | Owner | required | 2026-04-18 23:57 | 2026-05-02 23:57 | None | 0% | Should
Monitoring | Not Started | Monitoring | admin | Medium | Owner | required | 2026-04-18 23:57 | 2026-05-02 23:57 | None | 0%
- Splunk Forwarder Configured | Not Started | Monitoring | admin | Medium | Owner | required | 2026-04-18 23:57 | 2026-05-02 23:57 | None | 0% | Should
- Splunk Dashboard | Not Started | Monitoring | admin | Medium | Owner | required | 2026-04-18 23:57 | 2026-05-02 23:57 | None | 0%
- Dynatrace Telemetry | Not Started | Monitoring | admin | Medium | Owner | required | 2026-04-18 23:57 | 2026-05-02 23:57 | None | 0% | Want

## Retired VM Cleanup
Action Item | Status | Phase | Category | Priority | Owner | Responsibility | Assigned Date | Due Date | Challenges | Progress % | Priority Class
Project Start | Not Started | Planning | admin | Medium | Owner | required | 2026-04-18 23:57 | 2026-05-02 23:57 | None | 0%
- Create Project Sheet | Not Started | Planning | admin | Medium | Owner | required | 2026-04-18 23:57 | 2026-05-02 23:57 | None | 0%
- Create Confluence Project Page | Not Started | Planning | admin | Medium | Owner | required | 2026-04-18 23:57 | 2026-05-02 23:57 | None | 0%
- Review Acceptance Criteria | Not Started | Planning | admin | Medium | Owner | required | 2026-04-18 23:57 | 2026-05-02 23:57 | None | 0%
Requirements Gathering | Not Started | Requirements | admin | Medium | Owner | required | 2026-04-18 23:57 | 2026-05-02 23:57 | None | 0%
- Meeting with Stakeholders | Not Started | Requirements | admin | Medium | Owner | required | 2026-04-18 23:57 | 2026-05-02 23:57 | None | 0%
- Refine Acceptance Criteria | Not Started | Requirements | admin | Medium | Owner | required | 2026-04-18 23:57 | 2026-05-02 23:57 | None | 0%
- Define MVP | Not Started | Requirements | admin | Medium | Owner | required | 2026-04-18 23:57 | 2026-05-02 23:57 | None | 0%
- Define FR, NFR, AC, US | Not Started | Requirements | admin | Medium | Owner | required | 2026-04-18 23:57 | 2026-05-02 23:57 | None | 0%
Design | Not Started | Design | admin | Medium | Owner | required | 2026-04-18 23:57 | 2026-05-02 23:57 | None | 0%
- Draw C4 Docs | Not Started | Design | admin | Medium | Owner | required | 2026-04-18 23:57 | 2026-05-02 23:57 | None | 0%
Implementation | Not Started | Implementation | admin | Medium | Owner | required | 2026-04-18 23:57 | 2026-05-02 23:57 | None | 0%
- Create Doctor Patient | Not Started | Implementation | admin | Medium | Owner | required | 2026-04-18 23:57 | 2026-05-02 23:57 | None | 0%
- PR to Main | Not Started | Implementation | admin | Medium | Owner | required | 2026-04-18 23:57 | 2026-05-02 23:57 | None | 0%
- ReadMe | Not Started | Implementation | admin | Medium | Owner | required | 2026-04-18 23:57 | 2026-05-02 23:57 | None | 0%
Monitoring | Not Started | Monitoring | admin | Medium | Owner | required | 2026-04-18 23:57 | 2026-05-02 23:57 | None | 0%
- Splunk Forwarder Configured | Not Started | Monitoring | admin | Medium | Owner | required | 2026-04-18 23:57 | 2026-05-02 23:57 | None | 0%
- Splunk Dashboard | Not Started | Monitoring | admin | Medium | Owner | required | 2026-04-18 23:57 | 2026-05-02 23:57 | None | 0%
- Dynatrace Telemetry | Not Started | Monitoring | admin | Medium | Owner | required | 2026-04-18 23:57 | 2026-05-02 23:57 | None | 0%

## Zerto Scripts
Action Item | Status | Phase | Category | Priority | Owner | Responsibility | Assigned Date | Due Date | Challenges | Progress % | Priority Class
Project Start | Not Started | Planning | admin | Medium | Owner | required | 2026-04-18 23:57 | 2026-05-02 23:57 | None | 0%
- Create Project Sheet | Not Started | Planning | admin | Medium | Owner | required | 2026-04-18 23:57 | 2026-05-02 23:57 | None | 0%
- Create Confluence Project Page | Not Started | Planning | admin | Medium | Owner | required | 2026-04-18 23:57 | 2026-05-02 23:57 | None | 0%
- Review Acceptance Criteria | Not Started | Planning | admin | Medium | Owner | required | 2026-04-18 23:57 | 2026-05-02 23:57 | None | 0%
Requirements Gathering | Not Started | Requirements | admin | Medium | Owner | required | 2026-04-18 23:57 | 2026-05-02 23:57 | None | 0%
- Meeting with Stakeholders | Not Started | Requirements | admin | Medium | Owner | required | 2026-04-18 23:57 | 2026-05-02 23:57 | None | 0%
- Refine Acceptance Criteria | Not Started | Requirements | admin | Medium | Owner | required | 2026-04-18 23:57 | 2026-05-02 23:57 | None | 0%
- Define MVP | Not Started | Requirements | admin | Medium | Owner | required | 2026-04-18 23:57 | 2026-05-02 23:57 | None | 0%
- Define FR, NFR, AC, US | Not Started | Requirements | admin | Medium | Owner | required | 2026-04-18 23:57 | 2026-05-02 23:57 | None | 0%
Design | Not Started | Design | admin | Medium | Owner | required | 2026-04-18 23:57 | 2026-05-02 23:57 | None | 0%
- Draw C4 Docs | Not Started | Design | admin | Medium | Owner | required | 2026-04-18 23:57 | 2026-05-02 23:57 | None | 0%
Implementation | Not Started | Implementation | admin | Medium | Owner | required | 2026-04-18 23:57 | 2026-05-02 23:57 | None | 0%
- Create Doctor Patient | Not Started | Implementation | admin | Medium | Owner | required | 2026-04-18 23:57 | 2026-05-02 23:57 | None | 0%
- PR to Main | Not Started | Implementation | admin | Medium | Owner | required | 2026-04-18 23:57 | 2026-05-02 23:57 | None | 0%
- ReadMe | Not Started | Implementation | admin | Medium | Owner | required | 2026-04-18 23:57 | 2026-05-02 23:57 | None | 0%
Monitoring | Not Started | Monitoring | admin | Medium | Owner | required | 2026-04-18 23:57 | 2026-05-02 23:57 | None | 0%
- Splunk Forwarder Configured | Not Started | Monitoring | admin | Medium | Owner | required | 2026-04-18 23:57 | 2026-05-02 23:57 | None | 0%
- Splunk Dashboard | Not Started | Monitoring | admin | Medium | Owner | required | 2026-04-18 23:57 | 2026-05-02 23:57 | None | 0%
- Dynatrace Telemetry | Not Started | Monitoring | admin | Medium | Owner | required | 2026-04-18 23:57 | 2026-05-02 23:57 | None | 0%